## R-III
Stakeholder Group | Role in the Project | Influence (High/Medium/Low) | Interest (High/Medium/Low) | Involvement (Active/Passive)
Owners/Sponsors/Executive Heads | Fundings/Investments | High | High | Passive
Hospital Administration | Overall project sponsor; provides approval and funding | High | High | Active
Doctors | Provide medical services; key users of patient records | High | High | Active
Nurses | Support patient care; coordinate with doctors/pharmacy | Medium | High | Active
IT Department | Implement and maintain technology solutions | High | Medium | Active
Pharmacy Staff | Manage medications and coordinate with doctors/nurses | Medium | Medium | Active
Patients | End-users of hospital services; experience improvements | Low | High | Passive

## P-I Grid
Power
| Owners/Sponsors/Executive Heads | Hospital Administration
| IT Department | Doctors
Patients
| Support Staffs | Nurses
Pharmacy Staff
Interest

## RACI Matrix
Task/Deliverable | Owners/Executive Heads | Hospital Administration | Doctors | Nurses | IT Department | Pharmacy Staff | Patients
Define project goals | A/C/I | A | C | C | C | C | I
Funding/Investment | R/A/C/I | I | I | I | I | I | I
Gather requirements | C/I | C | R | R | C | R | I
Design new patient management system | A/C/I | A | C | C | R | C | I
Implement new communication platform | A/C/I | A | C | C | R | C | I
Change management & Training programs | A/C/I | A | R | R | R | R | I
Monitor Results & Optimize processes | A/C/I | A | R | R | R | R | I

## RACI_draft
Task/Deliverable | Hospital Administration | Doctors | Nurses | IT Department | Pharmacy Staff | Patients
Project Initiation and Approval | R | C | I | I | I | I
Requirements Gathering | A | C | C | R | C | I
Process Mapping | C | A | C | R | C | I
Technology Assessment and Selection | A | C | I | R | I | I
Implementation Oversight | A | I | I | R | I | I
Training and Change Management | A | I | A | R | C | I
Testing and Validation | C | A | C | R | C | I
Go-Live and Monitoring | A | C | A | R | C | I
Patient Feedback Collection | C | I | I | I | I | A